## Overview
KTA REGISTRIES v0.1
Structured project memory for Knowledge → Action
Metric | Current Count
Approved/recorded changes
Recorded decisions
Active experiments
Parked ideas
Registry | Purpose | Authority | Notes
Change Registry | Tracks material product/governance changes and propagation | Authoritative for approved changes | Every promoted change gets an ID
Decision Registry | Tracks current product and governance decisions | Authoritative for decision history | Includes rationale and affected lanes
Experiment Registry | Tracks tests, hypotheses, metrics and outcomes | Non-authoritative until a decision is promoted | Experiments do not override CURRENT/CORE rules
Parking Lot | Stores useful ideas not currently being implemented | Non-authoritative | Revisit only when a return condition is met
Archive | Historical files live in the Drive Archive folder | Historical only | Does not define current product behavior

## Change Registry
ID | Date | Area | Observation / Trigger | Approved Change | Status | Evidence / Reason | Affected Systems | Version
KTA-001 |  | Governance | The project needs continuity and explicit change control from the beginning. | Adopt lane-based governance, idea statuses, impact tracking, propagation, versioning, handoffs and archive. | CORE | Explicitly approved by the user. | All project lanes | v0.1
KTA-002 |  | Continuity | ChatGPT Plus limits can force work to continue in a replacement chat. | No material project knowledge may depend on a single chat; use current-state snapshots, handoffs and canonical artifacts. | CORE | Explicitly approved by the user. | All project lanes | v0.1
KTA-003 |  | Storage | Chat history and memory should not be the sole project database. | Use Google Drive as the durable external source of truth for authoritative Knowledge → Action project state. | CORE | Explicitly approved by the user. | Master Control, Registries, Handoffs, Archive | v0.1
KTA-004 |  | Governance / Storage | Work moved to Claude Code, which writes to git; the Drive originals were not reachable from the session (AR-01). Owner decision D1. | Session Independence Rule (any AI session, any tool) and the Dual-Layer Source of Truth: Git is the canonical active development workspace; Drive is the canonical governance/release mirror and the independent recovery layer; releases carry a Git tag plus a Drive bundle with a SHA-256 manifest; a conflict-resolution rule is defined. Operational mode: manual release (D1 option B). Amends KTA-002 and KTA-003. | CORE | Explicitly approved by the owner, 2026-09-29 (D1, option B). | Constitution, Source Manifest, CLAUDE.md, Current State, all lanes | v0.1-r1
KTA-005 |  | Architecture / Data model | The Blueprint data model lacked TaskMap and other Lane 02 objects; Personalization was drawn as a pipeline stage; the Lane 02/05 boundary was unclear (AR-10, AR-04, AR-05). Owner decision D3. | Blueprint reconciled: data objects now include TaskMap, UncertaintyItem (incl. ResearchQuestion), FeedbackRecord and AdaptationDecision; Mission is a versioned Mission Packet; Outcome is an aggregate. Personalization is described as a property of planning and adaptation. Lane 02 owns the first experiment and check-in interface; Lane 05 owns ongoing adaptation. | CURRENT | Approved by the owner, 2026-09-29 (D3, option A), conditional on Lane 02 acceptance (D5). | Blueprint, Lane Map, Lanes 02, 03, 04, 05, 06 | v0.1-r1
KTA-006 |  | Privacy / Safety | The most natural experiment ('try AI on your real task') can expose confidential work information; KTA itself is an AI environment (AR-08). Owner decision D2. | Confidential Information Boundary added to the Blueprint's Core Product Principles as CORE. Implementation rules P1–P7 are recorded as CURRENT in DEC-009, with P1 revised per D2. | CORE | Principle approved by the owner, 2026-09-29 (D2). | Blueprint, Lanes 02, 05, 06, 07, pilot consent, checker | v0.1-r1
KTA-007 |  | Metrics | Meaningful Action Rate as worded can be satisfied by 'felt useful' (AR-15). Owner decision D4. | Refined Decision-Useful Action Rate adopted as the PROVISIONAL primary candidate under V0 evaluation. MAR is retained for comparison, together with the supporting and guardrail metrics. The safety gate is kept separate: serious harm does not invalidate DUAR, but it independently triggers the gate. Previous DEC-005 wording: 'Use Meaningful Action Rate as the provisional North Star metric.' | PROVISIONAL | Approved by the owner, 2026-09-29 (D4, option A with the refinement #8 amendment). | Blueprint, Current State, DEC-005, Lanes 05, 07 | v0.1-r1
KTA-008 |  | Lane 02 / Release | Lane 02 v0.1 was specified and stress-tested; the acceptance packet was reviewed. Owner decisions D5 and D6. | Lane 02 Mission Generation Engine v0.1 accepted with repairs R1–R5 (completed). Released as KTA-REL-0.1. The bundle SHA-256 is recorded in 06_RELEASES/RELEASE_LOG.md. The blind/adversarial evaluation design (EXP-V0-00) is authorized. | CURRENT | Approved by the owner, 2026-09-29 (D5, D6). Validation suite green before release. | Lanes 02, 05, 07, 08; Current State; Blueprint | v0.1-r1

## Experiment Registry
ID | Created | Hypothesis | Audience / Cohort | Method | Primary Metric | Result | Status | Decision / Learning | Affected Rules
EXP-V0-00 |  | Specs plus the frozen drafting prompt produce safe, grounded, differentiated packets on unseen cases (pass bar: acceptance packet §6). | 16 unseen cases: 3 owner seeds + 13 isolated-session cases; 6 dev / 10 sealed | Frozen drafting prompt → checker → blind scoring against captured LLM baselines; red-team intakes | Pass bar (0 safety violations; ≥60% blind actionability preference; ≤10% swap failures) |  | PLANNED | Protocol: 03_CURRENT_WORK/BLIND_EVAL_PROTOCOL_v0.1.md | DEC-010, DEC-008
EXP-V0-01 |  | After one loop, users value a KTA packet more than a longer generic LLM answer to the same goal. | V0 pilot cohort (6–8) | Randomized-order comparison with 2 verbatim LLM baselines at check-in | LLM-Baseline Preference |  | NOT STARTED |  | DEC-005
EXP-V0-02 |  | Attempt rate differs by experiment archetype and by baseline confidence (the audit-first 'homework' risk, FM-14). | V0 pilot cohort | Descriptive comparison | Attempt rate |  | NOT STARTED |  | DEC-010
EXP-V0-03 |  | Self-reported time shares are accurate to within one band for most tasks. | V0 participants who run an audit | DQ-07 estimates vs audit results | Band agreement |  | NOT STARTED |  | DEC-010
EXP-V0-04 |  | DUAR is a better decision metric than MAR for KTA (discrimination, resistance to gaming, relation to real-world decisions). | V0 pilot cohort | Compute both via tools/kta_metrics.py; review at the V0 decision gate | DUAR vs MAR comparison |  | NOT STARTED |  | DEC-005

## Decision Registry
ID | Date | Decision Area | Decision | Status | Rationale | Affected Lanes | Validation State | Version
DEC-001 |  | Product Direction | Build Knowledge → Action as an outcome-oriented consumer product rather than only a content-production engine. | CURRENT | The reusable asset is the transformation from complex information to trustworthy understanding, action and feedback. | 00, 01, 02, 03, 04, 05, 06, 07 | User-approved product direction | v0.1
DEC-002 |  | Initial Market | Start with working adults adapting to AI-driven changes in their profession. | PROVISIONAL | The problem is current, broad, lower-risk than medical/legal use cases, and fits the Living Knowledge model. | 01, 02, 03, 07 | Needs V0 user validation | v0.1
DEC-003 |  | First Mission | Use 'Stay Valuable as AI Changes My Work' as the first canonical mission. | PROVISIONAL | It creates one focused end-to-end test of diagnosis, task mapping, explanation, action and adaptation. | 02, 03, 04, 05, 07 | Needs V0 user validation | v0.1
DEC-004 |  | Product Differentiation | Optimize for a useful result rather than merely a better AI answer. | CORE | The product should diagnose, verify, prioritize, intervene, observe outcomes and adapt; it should reduce prompt-engineering burden for consumers. | 01, 02, 03, 05, 06 | User-approved product principle | v0.1
DEC-005 |  | North Star Metric | North Star: Decision-Useful Action Rate (refined) is the PROVISIONAL primary candidate under V0 evaluation; Meaningful Action Rate is retained for comparison; supporting and guardrail metrics are retained. Not locked; decided at the V0 decision gate. The safety gate is separate from the metric. | PROVISIONAL | The original MAR can be satisfied by self-reported usefulness. DUAR measures whether recommended experiments produce interpretable, decision-relevant evidence; MAR is kept for comparison (KTA-007). | 05, 07 | Amended 2026-09-29 (KTA-007, owner D4). Both metrics are computed in the V0 pilot (tools/kta_metrics.py). | v0.1-r1
DEC-006 |  | Distribution | Treat THE OTHER VARIABLE as a potential public discovery/acquisition layer rather than the final destination of the system. | CURRENT | Public content can surface problems while Knowledge → Action provides individual diagnosis, mission guidance, action and feedback. | 00, 04, 07 | Strategic current direction | v0.1
DEC-007 |  | Privacy / Safety | Confidential Information Boundary: KTA must never require, request or encourage a person to enter confidential employer, client, customer or other organizational information into an AI environment its owner has not approved — including KTA itself. KTA works from abstraction, redaction and the minimum necessary context. | CORE | A trust boundary that does not depend on experiment results (AR-08, D2). | All lanes | Owner-approved principle | v0.1-r1
DEC-008 |  | Lane 02 behavioral invariants | Lane 02 behavioral invariants B-01..B-14 (scope triage first; confidential boundary; no automation-risk scores; evidence gate; grounding; mandatory omission; routed unknowns; pre-registered observable experiments; attention budget; harm first; no pushing; identity protection; revision traceability; n=1 evidence stays personal). Full list: acceptance packet §3a. | CURRENT | Behavioral rules implementing CORE principles; they hold regardless of pilot results. | 02, 03, 04, 05, 06, 07 | Simulation and checker; blind evaluation next | v0.1-r1
DEC-009 |  | Privacy / Safety | Confidential-information implementation rules. P1 intake abstraction: coarse, derived, non-confidential workflow quantities are allowed (approximate hours/week, frequency, approximate time share, rough counts, self-estimated proportions); confidential or proprietary organizational figures, documents, employer/client/customer names, account identifiers, sensitive internal metrics and other protected work information are never requested; prefer abstraction, redaction, ranges and approximations; anything volunteered that appears confidential is removed before LLM drafting (INV-16). P2 work material only in approved tools with confirmed scope (INV-08). P3 unknown scope = not approved. P4 current-habit cross-check without blame. P5 a prohibitive policy allows off-work practice only on public or synthetic material. P6 real pilot data never stored in Git. P7 only controlled-vocabulary fields aggregated, and only with opt-in. | CURRENT | Implements DEC-007; the rules may evolve with evidence (D2, P1 revised by the owner). | 02, 05, 06, 07 | Enforced by INV-08/INV-16 and the checker lint | v0.1-r1
DEC-010 |  | Lane 02 specification | Lane 02 Mission Generation Engine v0.1 (specs at 0.1-rev2 after repairs R1–R5) and its parameters (acceptance packet §3b) adopted as the specification for blind evaluation and the V0 pilot. | PROVISIONAL | Stress-tested in simulation; parameters are tunable after evidence. | 02, 03, 04, 05, 07 | Simulation only; blind evaluation and pilot pending | v0.1-r1
DEC-011 |  | Validation process | Blind/adversarial evaluation before any real-human pilot. 3 human seed cases from the owner, plus cases generated in an isolated AI session with no access to KTA specs; a dev/sealed split; sealed cases never exposed to the builder before the drafting prompt is frozen; blind scoring by a separate evaluator with no source labels. | CURRENT | Counters the closed-loop validation limitation (FM-17; acceptance packet §6). | 02, 07, 08 | Authorized; not started | v0.1-r1

## Parking Lot
ID | Date Added | Idea | Why It May Matter | Status | Affected Lanes | Return Condition | Notes
PARK-001 |  | Reuse Truthcast (same repo) claim extraction, research and 'bar' filter as a Lane 03 Evidence Engine prototype | It already implements a strict evidence filter and plain-language output | PARKED | 03, 06 | When Lane 03 specification starts | AR-25
PARK-002 |  | Reconsider the public mission name 'Stay Valuable…' (threat framing) | Users may be leverage-, transition- or clarify-minded | PARKED | 01, 04, 07 | When V0 goal-archetype frequencies are known | AR-23
PARK-003 |  | Soften the Core Promise wording 'will determine what matters' | It overclaims certainty compared with the explicit-uncertainty principle | PARKED | 01, 07 | Before any public copy | AR-24
PARK-005 |  | v0.2 field renames: first_experiment → current_experiment; employer_ai_policy → work_material_rules | Clearer semantics (FM-10) | PARKED | 02, 06 | Next contract revision | PARK-004 absorbed into EXP-V0-00